## ActivityLog
|  | Kayen | Lincoln | Takuya | Vick
2016-09-01 | Thu |  |  | Not successful retrieving real time taxi availability data from https://data.gov.sg even after creating account. Switching to https://www.mytransport.sg to get taxi availability. Managed to get data from website but not successful to do it in GAE.
2016-09-02 | Fri |  |  | Practicing Git. Linking local files to Github https://github.com/tiwagaki/rad_assignment2
2016-09-03 | Sat |  |  | Successfully getting and displaying JSON file (taxi locations) from http://datamall2.mytransport.sg/.
2016-09-04 | Sun |  | Contribute to repository via Git | JINJA2 template implemented. Current location is successfully displayed via Geolocation api. | Learn Google App Engine code
2016-09-05 | Mon |  |  | Scrum meeting to share progress and to decide what to be done to complete Sprint 1.
2016-09-06 | Tue |  |  | Scrum meeting to share progress and to decide what to be done to complete Sprint 1.
2016-09-07 | Wed |  |  | No Activity due to class
2016-09-08 | Thu |  |  | Scrum meeting to share progress and to decide what to be done to complete Sprint 1. Research on displaying location on Google Map based on longitude and latitude.
2016-09-09 | Fri
2016-09-10 | Sat
2016-09-11 | Sun
2016-09-12 | Mon
2016-09-13 | Tue
2016-09-14 | Wed
2016-09-15 | Thu
2016-09-16 | Fri
2016-09-17 | Sat
2016-09-18 | Sun
2016-09-19 | Mon
2016-09-20 | Tue
2016-09-21 | Wed
2016-09-22 | Thu
2016-09-23 | Fri
2016-09-24 | Sat
2016-09-25 | Sun
2016-09-26 | Mon
2016-09-27 | Tue
2016-09-28 | Wed
2016-09-29 | Thu
2016-09-30 | Fri
Sprint1
Sprint2

## ProductBacklog
Pb_id | ProuctBacklog | User Story | Sprint | Delivery Date
1 | Current Location | I want to see my current location on google map. | 1
1
1
| Taxi Location | I want to see nearby available taxis on google map | 1
2
2
2
2

## SprintBacklog
Sb_id | Pb_id | SprintBacklog | Description | Sprint | Delivery Date
1 | 1 | JINJA2 | Use JINJA2 template for MVC framework | 1
2 | 1 | JavaScript | Implement current location in JavaScript in accordance with Google Map API | 1
3 | 1 |  |  | 1
4
|  | TaxiAvailability API header | Need to get API key and other header information