## ActivityLog
|  | Kayen | Lincoln | Takuya | Vick
2016-09-01 | Thu | Reviewing of lecture notes on JSON and XML coding format | Reviewing of lecture notes on JSON and XML coding format | Reviewing of lecture notes on JSON and XML coding format | Reviewing of lecture notes on JSON and XML coding format
2016-09-02 | Fri | Reviewing of lecture notes on JSON and XML coding format | Reviewing of lecture notes on JSON and XML coding format | Not successful retrieving real time taxi availability data from https://data.gov.sg even after creating account. Switching to https://www.mytransport.sg to get taxi availability. Managed to get data from website but not successful to do it in GAE. | Reviewing of lecture notes on JSON and XML coding format
2016-09-05 | Mon | Reviewing of lecture notes on JSON and XML coding format | Reviewing of lecture notes on JSON and XML coding format | Practicing Git. Linking local files to Github https://github.com/tiwagaki/rad_assignment2 | Reviewing of lecture notes on JSON and XML coding format
2016-09-06 | Tue |  | Researching on possible implementation ideas (Eg. Weather or Haze PSI) | Successfully getting and displaying JSON file (taxi locations) from http://datamall2.mytransport.sg/. | Learn Google App Engine code
2016-09-07 | Wed |  | Send request to NEA for APIs and Access https://www.nea.gov.sg/api/ | JINJA2 template implemented. Current location is successfully displayed via Geolocation api.
2016-09-08 | Thu |  | Reviewing of requested APIs and understanding provided Developer's Guide | Scrum meeting to share progress and to decide what to be done to complete Sprint 1.
2016-09-09 | Fri |  | Create Git account and requested access to https://github.com/tiwagaki/rad_assignment2 | Scrum meeting to share progress and to decide what to be done to complete Sprint 1.
2016-09-12 | Mon |  | Learn to use Git platform, contributed in pushing and pulling updated codes to share | Scrum meeting to share progress and to decide what to be done to complete Sprint 1. Research on displaying location on Google Map based on longitude and latitude.
2016-09-13 | Tue |  | Assist in documenting all workflow process into scrum logbook (Product & Sprint Backlog) | Development to display taxi locations on google map.
2016-09-14 | Wed |  | Assist in documenting all workflow process into scrum logbook (Product & Sprint Backlog) | Development to display taxi locations on google map. Facing difficulty to show current location and taxis on the same map, thus changed plan and trying to display current location and taxi locations on different maps.
2016-09-15 | Thu |  | Assist in documenting all workflow process into scrum logbook (Product & Sprint Backlog) | Development to display user's current location and taxi locations. Managed to display those on different map.
2016-09-16 | Fri
2016-09-19 | Mon
2016-09-20 | Tue
2016-09-21 | Wed
2016-09-22 | Thu
2016-09-23 | Fri
2016-09-26 | Mon
2016-09-27 | Tue
2016-09-28 | Wed
2016-09-29 | Thu
2016-09-30 | Fri
Sprint1
Sprint2

## ProductBacklog
PD_ID | ProuctBacklog | User Story | Delivery Date
1.1 | Current Location | I want to see my current location on google map. | 2016-09-09
1.2 | Taxi Location | I want to see nearby available taxis on google map | 2016-09-16
2.1
John overslept and is late for his work. He decided to take a cab there but due to the peak hour and bad weather condition, there are no available cabs on the road.

## SprintBacklog
PD_ID | SB_ID | Description | Delivery Date | PIC
1.1 | 1 | Research and understanding on free JSON/XML web service API | 2016-09-02 | All
1.1 | 2 | Request of web APIs from web service owner (Eg: Data gov, myTransport, Google Map, NEA) | 2016-09-02 | Lincoln & Takuya
1.1 | 3 | Choosing of selected choice of JSON examples | 2016-09-02 | Lincoln & Vick
1.1 | 4 | Tested raw data output from JSON example in HTML | 2016-09-02 | Lincoln & Vick
1.1 | 5 | Test codes with google app engine python | 2016-09-06 | Kayen & Takuya
1.1 | 6 | Implement and integrate basic code to display result | 2016-09-07 | Kayen & Takuya
1.1 | 7 | Use JINJA2 template for MVC framework for HTML file template | 2016-09-07 | Kayen & Takuya
1.1 | 8 | Documentation on all development progress for Logbook | 2016-09-09 | Lincoln & Vick
1.1 | 9 | Implemented current location in JavaScript in accordance with Google Map API | 2016-09-09 | Kayen & Takuya
1.2 | 10 | Request of web APIs from web service owner (Eg: Data gov, myTransport, Google Map, NEA) | 2016-09-12 | Lincoln & Takuya
1.2 | 11 | Implement code with current user location done in Product Backlog 1 | 2016-09-14 | Kayen & Takuya
1.2 | 12 | Tested raw data output from JSON example in HTML | 2016-09-15 | Lincoln & Vick
1.2 | 13 | Test codes with google app engine python | 2016-09-15 | Kayen & Takuya
1.2 | 14 | Documentation on all development progress for Logbook | 2016-09-16 | Lincoln & Vick
1.2 | 15 | Implement and integrate basic code to display result | 2016-09-16 | Kayen & Takuya
project inception, monoitoring and key milestones
planning
development and testing
closeout