## ActivityLog
|  | Kayen | Lincoln | Takuya | Vick
2016-09-01 | Thu |  |  | Not successful retrieving real time taxi availability data from https://data.gov.sg even after creating account. Switching to https://www.mytransport.sg to get taxi availability. Managed to get data from website but not successful to do it in GAE.
2016-09-02 | Fri |  |  | Practicing Git. Linking local files to Github https://github.com/tiwagaki/rad_assignment2
2016-09-03 | Sat |  |  | Successfully getting and displaying JSON file (taxi locations) from http://datamall2.mytransport.sg/.
2016-09-04 | Sun |  | Contribute to repository via Git | JINJA2 template implemented. Current location is successfully displayed via Geolocation api. | Learn Google App Engine code
2016-09-05 | Mon |  |  | Scrum meeting to share progress and to decide what to be done to complete Sprint 1.
2016-09-06 | Tue |  |  | Scrum meeting to share progress and to decide what to be done to complete Sprint 1.
2016-09-07 | Wed |  |  | No Activity due to class
2016-09-08 | Thu |  |  | Scrum meeting to share progress and to decide what to be done to complete Sprint 1. Research on displaying location on Google Map based on longitude and latitude.
2016-09-09 | Fri |  |  | No Activity due to work
2016-09-10 | Sat |  |  | Development to display taxi locations on google map.
2016-09-11 | Sun |  |  | Development to display taxi locations on google map. Facing difficulty to show current location and taxis on the same map, thus changed plan and trying to display current location and taxi locations on different maps.
2016-09-12 | Mon |  |  | Development to display user's current location and taxi locations. Managed to display those on different map.
2016-09-13 | Tue
2016-09-14 | Wed
2016-09-15 | Thu
2016-09-16 | Fri
2016-09-17 | Sat
2016-09-18 | Sun
2016-09-19 | Mon
2016-09-20 | Tue
2016-09-21 | Wed
2016-09-22 | Thu
2016-09-23 | Fri
2016-09-24 | Sat
2016-09-25 | Sun
2016-09-26 | Mon
2016-09-27 | Tue
2016-09-28 | Wed
2016-09-29 | Thu
2016-09-30 | Fri
Sprint1
Sprint2

## ProductBacklog
Pb_id | ProuctBacklog | User Story | Sprint | Delivery Date
1 | Current Location | I want to see my current location on google map. | 1
1
1
2 | Taxi Location | I want to see nearby available taxis on google map | 1
2
2
2
2

## SprintBacklog
Sb_id | Pb_id | SprintBacklog | Description | Delivery Date
1 | 1 |  | Research and understanding on free JSON/XML web service API
2 | 1 |  | Discuss on real world issues and development of beneficial applications to society
3 | 1 |  | Survey of websites that contain implemented web services function (Eg: Banks Locator, LTA Traffic Cam, Weather PSI)
4 | 1 |  | Request of web APIs from web service owner (Eg: Data gov, myTransport, Google Map, NEA)
5 | 1 |  | Choosing of selected choice of JSON examples
6 | 1 |  | Tested raw data output from JSON example in HTML
7 | 1 |  | Decide on getting current user location with Google Map service
8 | 1 |  | Test codes with google app engine python
9 | 1 |  | Implement and integrate basic code to display result
10 | 1 | JINJA2 | Use JINJA2 template for MVC framework for HTML file template
11 | 1 | JavaScript | Implement current location in JavaScript in accordance with Google Map API
12 | 2 |  | Based on previous researches
13 | 2 |  | Discuss a possible practical idea to implement with current user location donein Product Backlog 1
14 | 2 |  | Tested raw data output from JSON example in HTML
15 | 2 |  | Decide on getting available taxi location with myTransport web service
16 | 2 |  | Test codes with google app engine python
17 | 2 |  | Implement and integrate basic code to display result
project inception, monoitoring and key milestones
planning
development and testing
closeout