## ActivityLog
|  | Kayen | Lincoln | Takuya | Vick
2016-09-01 | Thu |  |  | Not successful retrieving real time taxi availability data from https://data.gov.sg even after creating account. Switching to https://www.mytransport.sg to get taxi availability. Managed to get data from website but not successful to do it in GAE.
2016-09-02 | Fri |  |  | Practicing Git. Linking local files to Github https://github.com/tiwagaki/rad_assignment2
2016-09-03 | Sat |  |  | Successfully getting and displaying JSON file (taxi locations) from http://datamall2.mytransport.sg/.
2016-09-04 | Sun |  | Contribute to repository via Git | JINJA2 template implemented. Current location is successfully displayed via Geolocation api. | Learn Google App Engine code
2016-09-05 | Mon |  |  | Scrum meeting to share progress and to decide what to be done to complete Sprint 1.
2016-09-06 | Tue |  |  | Scrum meeting to share progress and to decide what to be done to complete Sprint 1.
2016-09-07 | Wed |  |  | No Activity due to class
2016-09-08 | Thu |  |  | Scrum meeting to share progress and to decide what to be done to complete Sprint 1. Research on displaying location on Google Map based on longitude and latitude.
2016-09-09 | Fri
2016-09-10 | Sat
2016-09-11 | Sun
2016-09-12 | Mon
2016-09-13 | Tue
2016-09-14 | Wed
2016-09-15 | Thu
2016-09-16 | Fri
2016-09-17 | Sat
2016-09-18 | Sun
2016-09-19 | Mon
2016-09-20 | Tue
2016-09-21 | Wed
2016-09-22 | Thu
2016-09-23 | Fri
2016-09-24 | Sat
2016-09-25 | Sun
2016-09-26 | Mon
2016-09-27 | Tue
2016-09-28 | Wed
2016-09-29 | Thu
2016-09-30 | Fri
Sprint1
Sprint2

## ProductBacklog
Pb_id | ProuctBacklog | User Story | Sprint | Delivery Date
1 | Current Location | I want to see my current location on google map. | 1
1
1
2 | Taxi Location | I want to see nearby available taxis on google map | 1
2
2
2
2

## SprintBacklog
Sb_id | Pb_id | SprintBacklog | Description | Delivery Date
1 | 1 |  | Research and understanding on free JSON/XML web service API
2 | 1 |  | Discuss on real world issues and development of beneficial applications to society
3 | 1 |  | Survey of websites that contain implemented web services function (Eg: Banks Locator, LTA Traffic Cam, Weather PSI)
4 | 1 |  | Request of web APIs from web service owner (Eg: Data gov, myTransport, Google Map, NEA)
5 | 1 |  | Choosing of selected choice of JSON examples
6 | 1 |  | Tested raw data output from JSON example in HTML
7 | 1 |  | Decide on getting current user location with Google Map service
8 | 1 |  | Test codes with google app engine python
9 | 1 |  | Implement and integrate basic code to display result
10 | 1 | JINJA2 | Use JINJA2 template for MVC framework for HTML file template
11 | 1 | JavaScript | Implement current location in JavaScript in accordance with Google Map API
12 | 2 |  | Based on previous researches
13 | 2 |  | Discuss a possible practical idea to implement with current user location donein Product Backlog 1
14 | 2 |  | Tested raw data output from JSON example in HTML
15 | 2 |  | Decide on getting available taxi location with myTransport web service
16 | 2 |  | Test codes with google app engine python
17 | 2 |  | Implement and integrate basic code to display result
project inception, monoitoring and key milestones
planning
development and testing
closeout