## ActivityLog
|  | Kayen (Developer -> Developer) | Lincoln (Software Architect -> UI Designer) | Takuya (Developer -> Scrum Master) | Vick (Scrum Master -> UI Designer)
2016-09-01 | Thu | Developer Reviewing of lecture notes on JSON and XML coding format | Software Architecht Reviewing of lecture notes on JSON and XML coding format | Developer Not successful retrieving real time taxi availability data from https://data.gov.sg even after creating account. Switching to https://www.mytransport.sg to get taxi availability. Managed to get data from website but not successful to do it in GAE. | Scrum Master Reviewing of lecture notes on JSON and XML coding format
2016-09-02 | Fri | Reviewing of lecture notes on JSON and XML coding format | Reviewing of lecture notes on JSON and XML coding format | Practicing Git. Linking local files to Github https://github.com/tiwagaki/rad_assignment2 | Reviewing of lecture notes on JSON and XML coding format
2016-09-03 | Sat |  |  | Successfully getting and displaying JSON file (taxi locations) from http://datamall2.mytransport.sg/.
2016-09-04 | Sun |  | Contribute to repository via Git | JINJA2 template implemented. Current location is successfully displayed via Geolocation api. | Learn Google App Engine code
2016-09-05 | Mon | Reviewing of lecture notes on JSON and XML coding format | Reviewing of lecture notes on JSON and XML coding format | Scrum meeting to share progress and to decide what to be done to complete Sprint 1. | Reviewing of lecture notes on JSON and XML coding format
2016-09-06 | Tue |  | Researching on possible implementation ideas (Eg. Weather or Haze PSI) | Scrum meeting to share progress and to decide what to be done to complete Sprint 1. | Learn Google App Engine code
2016-09-07 | Wed |  | Send request to NEA for APIs and Access https://www.nea.gov.sg/api/ | No Activity
2016-09-08 | Thu |  | Reviewing of requested APIs and understanding provided Developer's Guide | Scrum meeting to share progress and to decide what to be done to complete Sprint 1. Research on displaying location on Google Map based on longitude and latitude.
2016-09-09 | Fri |  | Create Git account and requested access to https://github.com/tiwagaki/rad_assignment2 | No Activity
2016-09-10 | Sat |  |  | Development to display taxi locations on google map.
2016-09-11 | Sun |  |  | Development to display taxi locations on google map. Facing difficulty to show current location and taxis on the same map, thus changed plan and trying to display current location and taxi locations on different maps.
2016-09-12 | Mon |  | Learn to use Git platform, contributed in pushing and pulling updated codes to share | Development to display user's current location and taxi locations. Managed to display those on different map.
2016-09-13 | Tue |  | Assist in documenting all workflow process into scrum logbook (Product & Sprint Backlog) | Development to display taxi locations on google map.
2016-09-14 | Wed |  | Assist in documenting all workflow process into scrum logbook (Product & Sprint Backlog) | Development to display taxi locations on google map. Facing difficulty to show current location and taxis on the same map, thus changed plan and trying to display current location and taxi locations on different maps.
2016-09-15 | Thu | Developer Reviewing of lecture notes on JSON and XML coding format | Assist in documenting all workflow process into scrum logbook (Product & Sprint Backlog) | Development to display user's current location and taxi locations. Managed to display those on different map.
2016-09-16 | Fri | Developer | UI Designer | Scrum Master No Activity | UI Designer
2016-09-17 | Sat |  |  | No Activity
2016-09-18 | Sun |  |  | Update Scrum_Log_Book. Planning scrum meeting agenda
2016-09-19 | Mon | Scrum meeting for progress reporting and to agree with product backlog and sprint backlog for sprint2. Document updated and agreed on demonstration of progress on 22nd. | Scrum meeting for progress reporting and to agree with product backlog and sprint backlog for sprint2. Document updated and agreed on demonstration of progress on 22nd. | Scrum meeting for progress reporting and to agree with product backlog and sprint backlog for sprint2. Document updated and agreed on demonstration of progress on 22nd. | Scrum meeting for progress reporting and to agree with product backlog and sprint backlog for sprint2. Document updated and agreed on demonstration of progress on 22nd.
2016-09-20 | Tue
2016-09-21 | Wed
2016-09-22 | Thu
2016-09-23 | Fri
2016-09-24 | Sat
2016-09-25 | Sun
2016-09-26 | Mon
2016-09-27 | Tue
2016-09-28 | Wed
2016-09-29 | Thu
2016-09-30 | Fri
Sprint1
Sprint2

## ProductBacklog
PB_ID | ProuctBacklog | User Story | Delivery Date
1.1 | Current Location | I want to see my current location on google map. | 2016-09-09
1.2 | Taxi Location | I want to see nearby available taxis on google map | 2016-09-16
2.1 | UI Design - Format | I want the application to be reasonably formatted | 2016-09-30
2.2 | UI Design - Colour | I want the application to be reasonably coloured | 2016-09-30
2.3 | Map Unification | I want to see the application to display only one map | 2016-09-30
2.4 | Distance Computation | I want to know the distance between current location and Taxi Location | 2016-09-30
John overslept and is late for his work. He decided to take a cab there but due to the peak hour and bad weather condition, there are no available cabs on the road.

## SprintBacklog
PB_ID | SB_ID | Description | Delivery Date | PIC
1.1 | 1 | Research and understanding on free JSON/XML web service API | 2016-09-02 | All
1.1 | 2 | Request of web APIs from web service owner (Eg: Data gov, myTransport, Google Map, NEA) | 2016-09-02 | Lincoln & Takuya
1.1 | 3 | Choosing of selected choice of JSON examples | 2016-09-02 | Lincoln & Vick
1.1 | 4 | Tested raw data output from JSON example in HTML | 2016-09-02 | Lincoln & Vick
1.1 | 5 | Test codes with google app engine python | 2016-09-06 | Kayen & Takuya
1.1 | 6 | Implement and integrate basic code to display result | 2016-09-07 | Kayen & Takuya
1.1 | 7 | Use JINJA2 template for MVC framework for HTML file template | 2016-09-07 | Kayen & Takuya
1.1 | 8 | Documentation on all development progress for Logbook | 2016-09-09 | Lincoln & Vick
1.1 | 9 | Implemented current location in JavaScript in accordance with Google Map API | 2016-09-09 | Kayen & Takuya
1.2 | 10 | Request of web APIs from web service owner (Eg: Data gov, myTransport, Google Map, NEA) | 2016-09-12 | Lincoln & Takuya
1.2 | 11 | Implement code with current user location done in Product Backlog 1 | 2016-09-14 | Kayen & Takuya
1.2 | 12 | Tested raw data output from JSON example in HTML | 2016-09-15 | Lincoln & Vick
1.2 | 13 | Test codes with google app engine python | 2016-09-15 | Kayen & Takuya
1.2 | 14 | Documentation on all development progress for Logbook | 2016-09-16 | Lincoln & Vick
1.2 | 15 | Implement and integrate basic code to display result | 2016-09-16 | Kayen & Takuya
2.1 | 15 | To demonstrate prototype UI design (format) on 22nd September | 2016-09-22 | Lincoln & Vick
2.2 | 16 | To demonstrate prototype UI design (Colour) on 22nd September | 2016-09-22 | Lincoln & Vick
2.3 | 17 | To demonstrate progress of Map Unification on 22nd September | 2016-09-22 | Kayen
2.4 | 18 | To demonstrate progress of Distance Computation (without unit conversion) on 22nd September | 2016-09-22 | Kayen
project inception, monoitoring and key milestones
planning
development and testing
closeout